## Test Checklist
Test ID | Module | Test Scenario | Test Steps / Input | Expected Result | Priority | Status | Actual Result / Evidence | Defect ID | Tester | Test Date | Automation Type | Coverage Refs | Notes
AUTH-001 | Authentication | Approved user login | Sign in with an approved Google account. | Redirects to Dashboard; login card disappears. | P0 | Pass (mocked) | Mocked E2E suite (desktop/tablet/mobile Chromium), 2026-10-12 - e2e/journeys/*.spec.ts; see docs/qa-report-2026-10-12.md |  | Automated (Playwright) | 2026-10-12 | Automated (mocked E2E) | A-01
AUTH-002 | Authentication | Authenticated /login redirect | Open #/login while already signed in. | Redirects to Dashboard; no login card inside app shell. | P0 | Pass (mocked) | Mocked E2E suite (desktop/tablet/mobile Chromium), 2026-10-12 - e2e/journeys/*.spec.ts; see docs/qa-report-2026-10-12.md |  | Automated (Playwright) | 2026-10-12 | Automated (mocked E2E) | A-07; J-01
AUTH-003 | Authentication | Session survives refresh | Refresh a protected route while session is valid. | Session restores; user remains authenticated. | P0 | Pass (mocked) | Mocked E2E suite (desktop/tablet/mobile Chromium), 2026-10-12 - e2e/journeys/*.spec.ts; see docs/qa-report-2026-10-12.md |  | Automated (Playwright) | 2026-10-12 | Automated (mocked E2E) | A-05
AUTH-004 | Authentication | Expired/revoked session | Use an expired/revoked test session and refresh. | Backend rejects session and app redirects to login. | P0 | Pass (mocked) | Mocked E2E suite (desktop/tablet/mobile Chromium), 2026-10-12 - e2e/journeys/*.spec.ts; see docs/qa-report-2026-10-12.md |  | Automated (Playwright) | 2026-10-12 | Automated (mocked E2E) | A-09 | SESSION_INVALID envelope returns user to the login card.
AUTH-005 | Authentication | Transient validation failure | Simulate timeout during startup validation. | Session is not immediately erased; recoverable warning/retry appears. | P1 | Pass (mocked) | Mocked E2E suite (desktop/tablet/mobile Chromium), 2026-10-12 - e2e/journeys/*.spec.ts; see docs/qa-report-2026-10-12.md |  | Automated (Playwright) | 2026-10-12 | Automated (mocked E2E) | A-08 | 502 envelope: session kept, warning shown, next sign-in recovers.
AUTH-006 | Authentication | Logout | Logout, then open a protected route. | Current session invalidated; protected route redirects to login. | P0 | Pass (mocked) | Mocked E2E suite (desktop/tablet/mobile Chromium), 2026-10-12 - e2e/journeys/*.spec.ts; see docs/qa-report-2026-10-12.md |  | Automated (Playwright) | 2026-10-12 | Automated (mocked E2E) | J-01 | Backend logout called; sessionStorage cleared; login shown.
AUTH-007 | Authentication | Multi-user session isolation | Use two browser profiles; log out of one account. | Other user's session remains valid. | P1 | Not Run |  |  |  |  | Manual (live) |  | Needs two browser profiles; manual multi-tab/profile check.
AUTH-008 | RBAC | Role authorization | Test ADMIN and non-admin archive/user-management actions. | UI and backend enforce permissions. | P0 | Pass (mocked) | Mocked E2E suite (desktop/tablet/mobile Chromium), 2026-10-12 - e2e/journeys/*.spec.ts; see docs/qa-report-2026-10-12.md |  | Automated (Playwright) | 2026-10-12 | Automated (mocked E2E) | A-14 | UI gating + forbidden-URL redirect verified across roles; backend enforcement of archive/user-management still needs a live retest.
HOME-001 | Shelter Homes | Metadata preview | Preview a valid source spreadsheet URL. | Home name, address, phone and available caretaker/participant details appear. | P0 | Pass (mocked) | Mocked E2E suite (desktop/tablet/mobile Chromium), 2026-10-12 - e2e/journeys/*.spec.ts; see docs/qa-report-2026-10-12.md |  | Automated (Playwright) | 2026-10-12 | Automated (mocked E2E) | B-02
HOME-002 | Shelter Homes | Missing metadata | Preview a workbook with missing home fields. | Only missing fields require manual input; warnings are clear. | P1 | Pass (mocked) | Mocked E2E suite (desktop/tablet/mobile Chromium), 2026-10-12 - e2e/journeys/*.spec.ts; see docs/qa-report-2026-10-12.md |  | Automated (Playwright) | 2026-10-12 | Automated (mocked E2E) | B-05 | Only missing fields prompt; found fields kept.
HOME-003 | Shelter Homes | Contact provenance | Caretaker exists but official home contact is absent. | Caretaker shown separately; not silently treated as official contact. | P1 | Pass (mocked) | Mocked E2E suite (desktop/tablet/mobile Chromium), 2026-10-12 - e2e/journeys/*.spec.ts; see docs/qa-report-2026-10-12.md |  | Automated (Playwright) | 2026-10-12 | Automated (mocked E2E) | B-03 | Caretaker listed separately; official contact input left empty with warning.
HOME-004 | Shelter Homes | Connect new source | Connect a valid unconnected test spreadsheet. | One home/source created; import result is truthful. | P0 | Pass (mocked) | Mocked E2E suite (desktop/tablet/mobile Chromium), 2026-10-12 - e2e/journeys/*.spec.ts; see docs/qa-report-2026-10-12.md |  | Automated (Playwright) | 2026-10-12 | Automated (mocked E2E) | C-01
HOME-005 | Shelter Homes | Connect succeeds, import fails | Use controlled test import failure. | Shows connected-but-sync-failed and Retry; no false success. | P0 | Pass (mocked) | Mocked E2E suite (desktop/tablet/mobile Chromium), 2026-10-12 - e2e/journeys/*.spec.ts; see docs/qa-report-2026-10-12.md |  | Automated (Playwright) | 2026-10-12 | Automated (mocked E2E) | C-02 | Connected-but-sync-failed outcome with backend reason + Retry.
HOME-006 | Shelter Homes | Retry import | Retry a failed initial import. | Reuses existing home/source IDs; no duplicate home. | P0 | Pass (mocked) | Mocked E2E suite (desktop/tablet/mobile Chromium), 2026-10-12 - e2e/journeys/*.spec.ts; see docs/qa-report-2026-10-12.md |  | Automated (Playwright) | 2026-10-12 | Automated (mocked E2E) | C-03 | Exactly 1 connect + 1 sync request asserted; no duplicate home.
HOME-007 | Shelter Homes | Reconnect active source | Connect an already connected active URL. | Existing home shown with View/Sync path. | P0 | Pass (mocked) | Mocked E2E suite (desktop/tablet/mobile Chromium), 2026-10-12 - e2e/journeys/*.spec.ts; see docs/qa-report-2026-10-12.md |  | Automated (Playwright) | 2026-10-12 | Automated (mocked E2E) | C-04 | ALREADY_CONNECTED outcome; no duplicate card.
HOME-008 | Shelter Homes | Archived source URL | Connect a source attached to an archived home. | Clear archived state and authorized restore path; no duplicate. | P0 | Pass (mocked) | Mocked E2E suite (desktop/tablet/mobile Chromium), 2026-10-12 - e2e/journeys/*.spec.ts; see docs/qa-report-2026-10-12.md |  | Automated (Playwright) | 2026-10-12 | Automated (mocked E2E) | C-05
HOME-009 | Shelter Homes | Invalid/inaccessible URL | Use malformed URL or inaccessible spreadsheet. | Structured error; no incomplete home/source created. | P1 | Pass (mocked) | Mocked E2E suite (desktop/tablet/mobile Chromium), 2026-10-12 - e2e/journeys/*.spec.ts; see docs/qa-report-2026-10-12.md |  | Automated (Playwright) | 2026-10-12 | Automated (mocked E2E) | B-06; B-07 | Inaccessible-sheet error and non-JSON/404 responses verified; typing a malformed URL is blocked by the browser input (manual variant).
HOME-010 | Shelter Homes | Metadata refresh | Change test sheet home metadata and sync. | UI reflects metadata returned by backend and documented override rules. | P1 | Blocked |  |  |  |  | Blocked (live backend) | D-02 | Requires a real Sheets sync round-trip changing backend contact values.
API-001 | API/Transport | HTTP 404/non-JSON | Reproduce failed connection request in DevTools. | Error shown; never reported as success; action/status/response captured. | P0 | Pass (mocked) | Mocked E2E suite (desktop/tablet/mobile Chromium), 2026-10-12 - e2e/journeys/*.spec.ts; see docs/qa-report-2026-10-12.md |  | Automated (Playwright) | 2026-10-12 | Automated (mocked E2E) | C-06 | HTML 404 page: could-not-confirm outcome, technical detail preserved, never success.
API-002 | API/Transport | Route/payload contract | Inspect preview, connect, sync and attendance Network requests. | Action, payload and response match deployed backend. | P0 | Not Run |  |  |  |  | Manual (live) |  | DevTools inspection against the deployed backend.
API-003 | API/Transport | Timeout and retry | Simulate slow non-destructive request. | Terminal error state; button returns idle; retry works. | P1 | Pass (mocked) | Mocked E2E suite (desktop/tablet/mobile Chromium), 2026-10-12 - e2e/journeys/*.spec.ts; see docs/qa-report-2026-10-12.md |  | Automated (Playwright) | 2026-10-12 | Automated (mocked E2E) | H-01 | Terminal error state + working retry verified (dashboard summary, attendance read); slow-network timing variant remains manual.
API-004 | API/Transport | Unauthorized API call | Use approved test tooling to call protected route without valid session. | Structured auth/permission error; no sensitive data leaked. | P0 | Not Run |  |  |  |  | Manual (live) |  | Unauthenticated/under-privileged API call test with approved tooling.
SYNC-001 | Synchronization | Source Sheet → app | Change test participant name/age/standard and run supported sync. | Correct participant updates; stable ID preserved. | P0 | Blocked |  |  |  |  | Blocked (live backend) |  | Real two-way Sheets write-back needs a disposable non-production backend + test spreadsheet (unavailable).
SYNC-002 | Synchronization | App → participant sheet | Edit participant fields in app and save. | Correct source row updates; unrelated cells/formulas remain intact. | P0 | Blocked |  |  |  |  | Blocked (live backend) |  | Real write-back to the participant sheet; unsafe against production.
SYNC-003 | Synchronization | Rename → Event-wise sheet | Rename participant registered for events. | Event-wise displayed name and valid dropdown options update. | P0 | Blocked |  |  |  |  | Blocked (live backend) |  | Real rename write-back + Event-wise sheet update.
SYNC-004 | Synchronization | Dropdown preservation | Open Event-wise Name dropdown after rename. | Validation remains usable; stale old name removed where applicable. | P0 | Blocked |  |  |  |  | Blocked (live backend) |  | Depends on a real rename round-trip.
SYNC-005 | Synchronization | Truthful sync verdict | Cause a controlled source write-back failure. | UI reports not synchronized with reason; no false success toast. | P0 | Blocked |  |  |  |  | Blocked (live backend) |  | Verdict strings are unit-pinned (164 vitest tests); live write-back failure needs a real backend.
SYNC-006 | Synchronization | Retry sheet reconciliation | Use Retry sheet write after partial failure. | Only verified stale cells reconciled; no duplicates/unrelated writes. | P1 | Blocked |  |  |  |  | Blocked (live backend) |  | Needs real partial-failure reconciliation.
SYNC-007 | Synchronization | Sync All Homes | Run across multiple active test homes, including one controlled failure. | Progress/results truthful; one failure doesn't hide others; archived homes excluded. | P0 | Blocked |  |  |  |  | Blocked (live backend) |  | Multi-home job lifecycle needs a real backend + multiple test homes.
SYNC-008 | Synchronization | Idempotent repeated sync | Run sync twice with no source changes. | No duplicate participants/registrations or unnecessary writes. | P0 | Blocked |  |  |  |  | Blocked (live backend) |  | Needs a real repeated sync round-trip.
SYNC-009 | Synchronization | Source change trigger | If installed, edit one source participant cell. | Correct participant updates; no trigger/write-back loop; audit/version correct. | P1 | Blocked |  |  |  |  | Blocked (live backend) |  | Trigger-based flow only exists in a deployed spreadsheet.
PART-001 | Participants | Participant list/home mapping | Compare sample app rows to source workbook. | Names and home assignments match; no stale/duplicate rows. | P0 | Pass (mocked) | Mocked E2E suite (desktop/tablet/mobile Chromium), 2026-10-12 - e2e/journeys/*.spec.ts; see docs/qa-report-2026-10-12.md |  | Automated (Playwright) | 2026-10-12 | Automated (mocked E2E) | J-03 | Page render + participant/home mapping verified with stub data; live source-workbook comparison pending.
PART-002 | Participants | Participant details | Open participant detail. | Gender, age, standard and level match source data. | P1 | Not Run |  |  |  |  | Not automated (mockable) |  | Candidate for a mocked E2E journey.
PART-003 | Participants | Event summary | Compare participant event names/categories/modes/counts to source/DB. | Names, category counts and active total match actual registrations. | P0 | Not Run |  |  |  |  | Not automated (mockable) | J-03 | Mockable with a getParticipantEventSummaries stub.
PART-004 | Participants | Add registration | Register eligible participant for an event. | App and correct Event-wise slot update; constraints enforced. | P0 | Not Run |  |  |  |  | Not automated (mockable)
PART-005 | Participants | Cancel registration | Cancel a registration through UI. | Active summary/roster updates; history retained; correct slot cleared. | P0 | Not Run |  |  |  |  | Not automated (mockable)
PART-006 | Participants | Registration limits | Test 7th event, 3rd category event and 4th solo event with test data. | Backend rejects invalid registration; no partial writes. | P0 | Not Run |  |  |  |  | Not automated (mockable)
PART-007 | Participants | Concurrent participant edit | Edit same participant from two sessions with same version. | Stale write conflicts; latest data reloaded; no silent overwrite. | P1 | Not Run |  |  |  |  | Not automated (mockable) |  | VERSION_CONFLICT pattern already proven for attendance (ATT-006).
EVENT-001 | Events | Event master list | Compare app event list to approved event master. | Expected events/categories/modes appear without duplicates. | P0 | Pass (mocked) | Mocked E2E suite (desktop/tablet/mobile Chromium), 2026-10-12 - e2e/journeys/*.spec.ts; see docs/qa-report-2026-10-12.md |  | Automated (Playwright) | 2026-10-12 | Automated (mocked E2E) |  | Catalogue listing verified in stubbed E2E; live master-list comparison pending.
EVENT-002 | Events | Event roster | Open event participant roster. | Only valid active registrations and active-home participants appear. | P0 | Not Run |  |  |  |  | Not automated (mockable)
EVENT-003 | Events | Archived roster filter | Archive disposable test home and open active roster. | Archived-home participants hidden from active roster; history preserved. | P0 | Not Run |  |  |  |  | Not automated (mockable) | E-03 | Needs archived-home roster semantics (live or richer stub).
ATT-001 | Attendance | Load saved attendance | Open event with existing marks. | Saved Present/Absent values appear, not all Not marked. | P0 | Pass (mocked) | Mocked E2E suite (desktop/tablet/mobile Chromium), 2026-10-12 - e2e/journeys/*.spec.ts; see docs/qa-report-2026-10-12.md |  | Automated (Playwright) | 2026-10-12 | Automated (mocked E2E) | F-01
ATT-002 | Attendance | Mark attendance | Mark Present/Absent and save. | Backend confirms save; UI shows persisted status. | P0 | Pass (mocked) | Mocked E2E suite (desktop/tablet/mobile Chromium), 2026-10-12 - e2e/journeys/*.spec.ts; see docs/qa-report-2026-10-12.md |  | Automated (Playwright) | 2026-10-12 | Automated (mocked E2E) | F-02
ATT-003 | Attendance | Attendance after reload | Save attendance and refresh/reopen event. | Saved value remains correct. | P0 | Pass (mocked) | Mocked E2E suite (desktop/tablet/mobile Chromium), 2026-10-12 - e2e/journeys/*.spec.ts; see docs/qa-report-2026-10-12.md |  | Automated (Playwright) | 2026-10-12 | Automated (mocked E2E) | F-02 | Persistence re-verified via forced re-read after retry; literal F5 step is manual.
ATT-004 | Attendance | Idempotent repeat mark | Save identical status twice. | No duplicate row/version bump/audit duplication as specified. | P1 | Pass (mocked) | Mocked E2E suite (desktop/tablet/mobile Chromium), 2026-10-12 - e2e/journeys/*.spec.ts; see docs/qa-report-2026-10-12.md |  | Automated (Playwright) | 2026-10-12 | Automated (mocked E2E) | F-03
ATT-005 | Attendance | Attendance update/version | Change existing mark with current expectedVersion. | Record updates in place; version increments once. | P0 | Pass (mocked) | Mocked E2E suite (desktop/tablet/mobile Chromium), 2026-10-12 - e2e/journeys/*.spec.ts; see docs/qa-report-2026-10-12.md |  | Automated (Playwright) | 2026-10-12 | Automated (mocked E2E) | F-04 | expectedVersion enforced by the stub; version increment asserted indirectly.
ATT-006 | Attendance | Stale attendance version | Two tabs update same record from same version. | Stale write gets VERSION_CONFLICT; latest value reloads. | P0 | Pass (mocked) | Mocked E2E suite (desktop/tablet/mobile Chromium), 2026-10-12 - e2e/journeys/*.spec.ts; see docs/qa-report-2026-10-12.md |  | Automated (Playwright) | 2026-10-12 | Automated (mocked E2E) | F-05 | Conflict message shown, latest value reloaded, buttons usable again.
ATT-007 | Attendance | Archived participant attendance | Attempt write for archived-home participant. | Backend rejects new write; history unchanged. | P0 | Pass (mocked) | Mocked E2E suite (desktop/tablet/mobile Chromium), 2026-10-12 - e2e/journeys/*.spec.ts; see docs/qa-report-2026-10-12.md |  | Automated (Playwright) | 2026-10-12 | Automated (mocked E2E) | F-07; E-04 | Backend rejection surfaced verbatim; nothing marked.
SCORE-001 | Scoring | Save/read score | Save score and reload event/participant. | Score persists and displays correctly. | P0 | Not Run |  |  |  |  | Not automated (mockable)
SCORE-002 | Scoring | Score version conflict | Update same score from two sessions. | Stale write rejected; current score reloaded. | P1 | Not Run |  |  |  |  | Not automated (mockable)
SCORE-003 | Scoring | Archived participant scoring | Attempt score for archived-home participant. | Backend rejects write; history preserved. | P0 | Not Run |  |  |  |  | Not automated (mockable)
TEAM-001 | Teams | Team membership persistence | Add valid member and reload. | Membership persists without duplicate member rows. | P1 | Not Run |  |  |  |  | Not automated (mockable)
TEAM-002 | Teams | Archived participant team gate | Add archived-home participant to team. | Backend rejects membership write. | P1 | Not Run |  |  |  |  | Not automated (mockable)
RESULT-001 | Results | Results consistency | Open results for known test scores. | Results match persisted scores and configured ranking rules. | P1 | Not Run |  |  |  |  | Not automated (mockable)
CERT-001 | Certificates | Certificate flow | List/generate certificate for test participant/event. | Correct participant/event; no duplicate issuance. | P2 | Not Run |  |  |  |  | Not automated (mockable)
REPORT-001 | Reports | Report totals | Compare report totals to underlying participant/registration/attendance/score records. | Totals match documented filters and records. | P1 | Not Run |  |  |  |  | Not automated (mockable) | I-02 | Reports page renders in the responsive sweep; data comparison not run.
ADMIN-001 | Archive | Archive impact preview | Preview archiving disposable test home. | Accurate counts; preview causes no writes. | P0 | Pass (mocked) | Mocked E2E suite (desktop/tablet/mobile Chromium), 2026-10-12 - e2e/journeys/*.spec.ts; see docs/qa-report-2026-10-12.md |  | Automated (Playwright) | 2026-10-12 | Automated (mocked E2E) | E-01
ADMIN-002 | Archive | Archive home | Archive disposable home as ADMIN. | Home moves to archived list; records preserved; excluded from active sync/rosters. | P0 | Pass (mocked) | Mocked E2E suite (desktop/tablet/mobile Chromium), 2026-10-12 - e2e/journeys/*.spec.ts; see docs/qa-report-2026-10-12.md |  | Automated (Playwright) | 2026-10-12 | Automated (mocked E2E) | E-02
ADMIN-003 | Archive | Restore home | Restore archived test home. | Home returns to active list; trigger reinstall need is stated accurately. | P1 | Pass (mocked) | Mocked E2E suite (desktop/tablet/mobile Chromium), 2026-10-12 - e2e/journeys/*.spec.ts; see docs/qa-report-2026-10-12.md |  | Automated (Playwright) | 2026-10-12 | Automated (mocked E2E) | E-05 | Verified restoring from the zero-active-homes state (rendering defect fixed).
ADMIN-004 | Archive | Non-admin archive restriction | Attempt archive as non-admin. | Action unavailable in UI and rejected by backend. | P0 | Retest |  |  |  |  | Automated (unit) |  | UI gate unit-covered (canArchive); E2E non-admin archive attempt + backend rejection pending.
ADMIN-005 | User Admin | Approval lifecycle | Request access, approve as ADMIN, then sign in. | Pending user blocked; approved user can log in. | P1 | Not Run |  |  |  |  | Not automated (mockable) | I-01 | Needs listUsers/approveUser stubs in the E2E backend router.
PERF-001 | Performance | Request fan-out | Inspect Network on Dashboard/Participants/Attendance loads. | No per-participant N+1 requests; duplicate requests avoided. | P1 | Not Run |  |  |  |  | Manual (live) |  | Duplicate requests partly disproven by stub request counting (HOME-006).
PERF-002 | Performance | Loading terminal states | Refresh major pages and trigger errors/retries. | Spinners/buttons always reach terminal state; safe data remains visible. | P1 | Retest | Mocked E2E suite (desktop/tablet/mobile Chromium), 2026-10-12 - e2e/journeys/*.spec.ts; see docs/qa-report-2026-10-12.md |  | Automated (Playwright) | 2026-10-12 | Automated (mocked E2E) | H-01; H-02 | Dashboard/homes/participants/attendance terminal states verified; remaining pages pending.
DATA-001 | Data Integrity | Duplicate prevention | Retry connection/import/sync/registration/attendance on test data. | No duplicate homes/sources/participants/registrations/attendance. | P0 | Not Run |  |  |  |  | Manual (live) |  | Duplicate prevention partly proven by HOME-006/ATT-004 mocked journeys.
DATA-002 | Data Integrity | Formula/validation preservation | Rename participant and inspect source sheet formulas/dropdowns. | Unrelated formulas, formatting and validation remain intact. | P0 | Not Run |  |  |  |  | Manual (live)
DATA-003 | Data Integrity | Audit history | Perform rename, registration, attendance and archive operations. | Expected audit entries present; no tokens/secrets logged. | P1 | Not Run |  |  |  |  | Manual (live)
DATA-004 | Data Integrity | Production safety | Review planned test data and actions. | No bulk reset/deletion; disposable test home/workbook used. | P0 | Not Run |  |  |  |  | Manual (live) |  | Review step before any live execution.
COMP-001 | Compatibility | Schema/routes | Compare deployed router/manifest with frontend actions; run backend verify. | Schema unchanged; all used actions exist and return expected contracts. | P0 | Not Run |  |  |  |  | Manual (live)
COMP-002 | Concurrency | Multi-user simultaneous writes | Two approved users edit different records simultaneously, then same record. | Independent changes persist; same-record stale update conflicts safely. | P1 | Not Run |  |  |  |  | Not automated (mockable)
AUTH-009 | Authentication | Sign-in success only after backend confirms | Sign in and observe the UI before the verification request resolves; then force a failure. | Sign-in success appears only after APPROVED + valid session; a failure is never shown as success. | P0 | Pass (mocked) | Mocked E2E suite (desktop/tablet/mobile Chromium), 2026-10-12 - e2e/journeys/*.spec.ts; see docs/qa-report-2026-10-12.md |  | Automated (Playwright) | 2026-10-12 | Automated (mocked E2E) | A-02
AUTH-010 | Authentication | No app shell behind the login card (unauthenticated) | Sign out and open the app root. | Only the login page renders - no sidebar/header/footer around it. | P0 | Pass (mocked) | Mocked E2E suite (desktop/tablet/mobile Chromium), 2026-10-12 - e2e/journeys/*.spec.ts; see docs/qa-report-2026-10-12.md |  | Automated (Playwright) | 2026-10-12 | Automated (mocked E2E) | A-04
AUTH-011 | Authentication | Refresh on #/login with a valid session | Sign in, navigate to #/login manually, press F5. | Startup validation recovers the session and lands on /dashboard; the shell never wraps the login card. | P0 | Pass (mocked) | Mocked E2E suite (desktop/tablet/mobile Chromium), 2026-10-12 - e2e/journeys/*.spec.ts; see docs/qa-report-2026-10-12.md |  | Automated (Playwright) | 2026-10-12 | Automated (mocked E2E) | A-06 | Covers the session-restore race fixed in app.ts.
AUTH-012 | Authentication | Unregistered Google account | Sign in with a valid Google identity that is not registered. | Honest NOT_REGISTERED panel; no session stored; no crash. | P0 | Pass (mocked) | Mocked E2E suite (desktop/tablet/mobile Chromium), 2026-10-12 - e2e/journeys/*.spec.ts; see docs/qa-report-2026-10-12.md |  | Automated (Playwright) | 2026-10-12 | Automated (mocked E2E) | A-10
AUTH-013 | Authentication | Identity-recovery login for a recovered user | Run runIdentityRecoveryCheck for the recovered account, then sign in live. | Recovered user signs in and receives the correct role. | P1 | Blocked |  |  |  |  | Blocked (live backend) | A-11 | Needs the Apps Script recovery routine + the real account (production data). Still pending on the user side.
AUTH-014 | RBAC | Role-filtered navigation and settings gating | Sign in as ADMIN and as CERTIFICATE_TEAM; inspect navigation, open #/settings directly as non-admin. | Each role sees only its permitted sections; #/settings is hidden and redirects non-admins to the dashboard. | P0 | Pass (mocked) | Mocked E2E suite (desktop/tablet/mobile Chromium), 2026-10-12 - e2e/journeys/*.spec.ts; see docs/qa-report-2026-10-12.md |  | Automated (Playwright) | 2026-10-12 | Automated (mocked E2E) | A-12; A-13
HOME-011 | Shelter Homes | Preview gated on a spreadsheet URL | Open Add shelter home; observe Connect button before/after entering a URL. | Preview/Connect stays disabled until a URL is entered. | P1 | Pass (mocked) | Mocked E2E suite (desktop/tablet/mobile Chromium), 2026-10-12 - e2e/journeys/*.spec.ts; see docs/qa-report-2026-10-12.md |  | Automated (Playwright) | 2026-10-12 | Automated (mocked E2E) | B-01
HOME-012 | Shelter Homes | Explicit caretaker contact prefills Contact Name | Preview a workbook whose metadata contains an explicit official contact. | The Contact Name input is prefilled from the explicit metadata (never from caretaker data). | P1 | Pass (mocked) | Mocked E2E suite (desktop/tablet/mobile Chromium), 2026-10-12 - e2e/journeys/*.spec.ts; see docs/qa-report-2026-10-12.md |  | Automated (Playwright) | 2026-10-12 | Automated (mocked E2E) | B-04
HOME-013 | Shelter Homes | Malformed URL client-side error | Type a syntactically invalid URL bypassing browser validation (e.g. via JS) and preview. | Client-side validation message; no request issued. | P2 | Not Run |  |  |  |  | Manual (mocked) | B-06 | The browser URL input normally blocks typing nonsense.
HOME-014 | Shelter Homes | Spreadsheet ID never exposed in the UI | Complete a connect and inspect the page body for the raw spreadsheet id. | The identifier is not shown anywhere in the user interface. | P1 | Pass (mocked) | Mocked E2E suite (desktop/tablet/mobile Chromium), 2026-10-12 - e2e/journeys/*.spec.ts; see docs/qa-report-2026-10-12.md |  | Automated (Playwright) | 2026-10-12 | Automated (mocked E2E) | B-08
HOME-015 | Shelter Homes | Ambiguous connect failure re-checks the homes list | Force the connect request to fail ambiguously (504/HTML) while the connection actually persisted. | The verification re-read finds the persisted home and reports ALREADY_CONNECTED; no false failure. | P0 | Pass (mocked) | Mocked E2E suite (desktop/tablet/mobile Chromium), 2026-10-12 - e2e/journeys/*.spec.ts; see docs/qa-report-2026-10-12.md |  | Automated (Playwright) | 2026-10-12 | Automated (mocked E2E) | C-07
HOME-016 | Shelter Homes | Friendly sync status labels (no raw codes) | Open the homes list with homes in different sync states. | Human-readable labels (e.g. Synced / Sync needed); raw backend codes appear only in diagnostics. | P0 | Pass (mocked) | Mocked E2E suite (desktop/tablet/mobile Chromium), 2026-10-12 - e2e/journeys/*.spec.ts; see docs/qa-report-2026-10-12.md |  | Automated (Playwright) | 2026-10-12 | Automated (mocked E2E) | D-01
API-005 | API/Transport | Technical detail only in diagnostics | Trigger backend failures on connect/preview/sync journeys. | Primary messages stay human-readable; raw codes/statuses appear only in the diagnostics detail line. | P1 | Pass (mocked) | Mocked E2E suite (desktop/tablet/mobile Chromium), 2026-10-12 - e2e/journeys/*.spec.ts; see docs/qa-report-2026-10-12.md |  | Automated (Playwright) | 2026-10-12 | Automated (mocked E2E) | D-03 | Verified for the connect/preview failure surfaces; other surfaces manual.
API-006 | API/Transport | Unknown/unmocked action is aborted, never faked | Call a frontend journey whose backend action is not registered in the test stub router. | The request is aborted at the network layer; the UI shows an honest empty/error state; the session is kept; no fabricated data. | P0 | Pass (mocked) | Mocked E2E suite (desktop/tablet/mobile Chromium), 2026-10-12 - e2e/journeys/*.spec.ts; see docs/qa-report-2026-10-12.md |  | Automated (Playwright) | 2026-10-12 | Automated (mocked E2E) |  | Guards the E2E suite itself against leaking to production.
ATT-008 | Attendance | Failed read shows error with a working Retry | Force listAttendance to fail; press Retry with the backend recovered. | Error replaces content honestly; Retry issues a real new request and recovers the saved marks. | P1 | Pass (mocked) | Mocked E2E suite (desktop/tablet/mobile Chromium), 2026-10-12 - e2e/journeys/*.spec.ts; see docs/qa-report-2026-10-12.md |  | Automated (Playwright) | 2026-10-12 | Automated (mocked E2E) | H-01
ATT-009 | Attendance | Failed save never reports success | Abort/mark-fail the save request for an attendance row. | Error is shown, no success message appears, the row returns to idle and can be retried. | P0 | Pass (mocked) | Mocked E2E suite (desktop/tablet/mobile Chromium), 2026-10-12 - e2e/journeys/*.spec.ts; see docs/qa-report-2026-10-12.md |  | Automated (Playwright) | 2026-10-12 | Automated (mocked E2E) | F-06
IMPORT-001 | Imports | Initial import summary is truthful | Connect a test workbook and read the import outcome. | initialImport attempted/status/counts reflect the backend response exactly; no invented numbers. | P0 | Pass (mocked) | Mocked E2E suite (desktop/tablet/mobile Chromium), 2026-10-12 - e2e/journeys/*.spec.ts; see docs/qa-report-2026-10-12.md |  | Automated (Playwright) | 2026-10-12 | Automated (mocked E2E) | C-01
ADMIN-006 | Archive | History preserved after archiving | Archive a test home with historical attendance/scores and inspect past records. | Historical records remain intact and attributable; nothing is deleted by archiving. | P1 | Blocked |  |  |  |  | Blocked (live backend) | E-06 | Requires real historical records; a stub can only re-assert itself.
A11Y-001 | Accessibility | axe smoke: no critical/serious violations on key routes | Run axe-core on login, dashboard, homes, participants, events, attendance (desktop). | Zero critical/serious violations. Found issues (aria-hidden focus, prohibited labels, name mismatch, unnamed selects, contrast) were fixed 2026-10-12. | P1 | Pass (mocked) | Mocked E2E suite (desktop/tablet/mobile Chromium), 2026-10-12 - e2e/journeys/*.spec.ts; see docs/qa-report-2026-10-12.md |  | Automated (Playwright) | 2026-10-12 | Automated (mocked E2E) |  | Smoke signal only - not a WCAG compliance statement.
A11Y-002 | Accessibility | Keyboard-only navigation | Traverse login and each main page using keyboard only. | All interactive controls reachable and operable; visible focus; no traps. | P1 | Not Run |  |  |  |  | Manual (mocked)
A11Y-003 | Accessibility | Screen-reader spot check | Spot-check key flows with a screen reader (NVDA/VoiceOver). | Names, roles and states announced correctly for nav, tables, dialogs and toasts. | P2 | Not Run |  |  |  |  | Manual (live)
SEC-001 | Security | Credential/token hygiene | Inspect sessionStorage, network payloads and logs during sign-in/out and API errors. | Session id stored only in sessionStorage; no tokens/secrets logged or rendered; session cleared on logout. | P0 | Pass (mocked) | Mocked E2E suite (desktop/tablet/mobile Chromium), 2026-10-12 - e2e/journeys/*.spec.ts; see docs/qa-report-2026-10-12.md |  | Automated (Playwright) | 2026-10-12 | Automated (mocked E2E) |  | Session-clear on logout verified; full secret-hygiene sweep manual.
SEC-002 | Security | XSS resistance of rendered data | Import/register test values containing HTML/script metacharacters; view them in lists/tables. | Values render as text; no script execution or HTML injection. | P1 | Not Run |  |  |  |  | Not automated (mockable)
RESP-001 | Responsive | No horizontal overflow on key routes | Sweep login/dashboard/homes/participants/events/attendance at desktop, tablet and mobile viewports. | No horizontal scrolling or clipped content at any emulated viewport. | P1 | Pass (mocked) | Mocked E2E suite (desktop/tablet/mobile Chromium), 2026-10-12 - e2e/journeys/*.spec.ts; see docs/qa-report-2026-10-12.md |  | Automated (Playwright) | 2026-10-12 | Automated (mocked E2E) |  | Emulated Chromium viewports (1280 / 768x1024 touch / Pixel 7).
RESP-002 | Responsive | Mobile navigation drawer | Open the app at mobile width; open the drawer and navigate to a section. | Drawer opens from the header menu button; navigation works; drawer closes after navigation. | P1 | Pass (mocked) | Mocked E2E suite (desktop/tablet/mobile Chromium), 2026-10-12 - e2e/journeys/*.spec.ts; see docs/qa-report-2026-10-12.md |  | Automated (Playwright) | 2026-10-12 | Automated (mocked E2E)
COMP-003 | Compatibility | Desktop Chromium E2E pass | Run the full Playwright suite on the desktop project. | All mocked journeys pass (2026-10-12: 44 journeys x 3 projects, 0 failures). | P0 | Pass (mocked) | Mocked E2E suite (desktop/tablet/mobile Chromium), 2026-10-12 - e2e/journeys/*.spec.ts; see docs/qa-report-2026-10-12.md |  | Automated (Playwright) | 2026-10-12 | Automated (mocked E2E)
COMP-004 | Compatibility | Mobile emulation pass (Pixel 7) | Run the suite on the mobile-chromium project. | All applicable journeys pass; drawer/nav assertions viewport-aware. | P1 | Pass (mocked) | Mocked E2E suite (desktop/tablet/mobile Chromium), 2026-10-12 - e2e/journeys/*.spec.ts; see docs/qa-report-2026-10-12.md |  | Automated (Playwright) | 2026-10-12 | Automated (mocked E2E)
COMP-005 | Compatibility | Tablet emulation pass (768x1024 touch) | Run the suite on the tablet-chromium project. | All applicable journeys pass at tablet size with touch enabled. | P1 | Pass (mocked) | Mocked E2E suite (desktop/tablet/mobile Chromium), 2026-10-12 - e2e/journeys/*.spec.ts; see docs/qa-report-2026-10-12.md |  | Automated (Playwright) | 2026-10-12 | Automated (mocked E2E)
COMP-006 | Compatibility | Real device validation | Smoke-test sign-in, dashboard, attendance and a sync read on physical Android + iOS devices/browsers. | Layouts and touch interactions hold on real devices; no emulation-only artifacts. | P2 | Not Run |  |  |  |  | Manual (live) |  | Emulation is not real-device testing.
DATA-005 | Data Integrity | Failed read honesty (no fabricated or stale-as-current data) | Force dashboard/homes/participants reads to fail; observe the page; then retry. | Content is replaced with an honest error + Retry (established design); nothing is fabricated or blanked; session is kept; retry recovers. | P0 | Pass (mocked) | Mocked E2E suite (desktop/tablet/mobile Chromium), 2026-10-12 - e2e/journeys/*.spec.ts; see docs/qa-report-2026-10-12.md |  | Automated (Playwright) | 2026-10-12 | Automated (mocked E2E) | H-02

## Execution Guide
Nakshatra 2026 — Technical Test Execution Guide
Purpose | Track live acceptance tests after the latest backend is deployed and the frontend is published.
Safety | Use a disposable test home/workbook. Do not bulk-delete production data or reset attendance/scoring history.
Status values | Not Run ¦ Pass ¦ Fail ¦ Blocked ¦ Retest ¦ Pass (mocked)
P0 | Release-blocking. Execute first and resolve failures before production acceptance.
P1 | Important reliability, concurrency and performance checks.
P2 | Lower-priority checks such as certificate edge cases.
Evidence | For API errors, record sanitized action, status, response and timestamp. Never record tokens, secrets or raw session credentials.
Offline vs live | Automated unit tests do not prove deployed Apps Script, real Sheets permissions, triggers or concurrent writes.
Suggested order | AUTH → HOME → API → SYNC → PARTICIPANTS/EVENTS → ATTENDANCE → SCORING/TEAMS → ARCHIVE/ADMIN → REPORTS/CERTIFICATES → PERFORMANCE/DATA.
Result entry | Record actual result, evidence, defect ID, tester and test date for each executed case.
Pass (mocked) | The case was executed successfully in the stubbed E2E environment (local dev server + intercepted backend, Chromium desktop/tablet/mobile emulation) on 2026-10-12. The live deployment still needs final acceptance before marking plain Pass.
Automation Type | Values: Automated (mocked E2E) = Playwright journey with stubbed backend; Automated (unit) = vitest; Manual (live) = human test against the deployed backend; Manual (mocked) = human test in the stubbed environment; Not automated (mockable) = candidate for future E2E automation; Blocked (live backend) = impossible today without real Apps Script/Sheets/OAuth.
Mocked vs live | Mocked E2E proves frontend behavior and error honesty, not deployed Apps Script contracts, real Google sign-in, real Sheets read/write, triggers or concurrent multi-user writes. Live results require a disposable test spreadsheet + test home.
Desktop / mobile | Responsive checks ran as Chromium emulation: desktop 1280px, tablet 768x1024 (touch) and mobile Pixel 7. Emulation is not real-device testing - validate once on physical Android/iOS devices before release (COMP-006).
Safe test data | Use a disposable test home and a disposable Google Sheet with synthetic data (fixture data uses example.com). Never bulk-delete production data, never run destructive writes against production, and record no tokens/secrets/session credentials in evidence.
Coverage map | The 'Coverage Map' sheet traces every requirement in docs/manual-test-checklist-2026-10-12.csv (A-01..J-03) plus extra areas (security, accessibility, responsive) to one or more Test IDs with verification status.

## Coverage Map
Ref | Area | Requirement / coverage statement | Test Case ID(s) | Status | Notes
A-01 | Sign-in | Approved sign-in redirects to dashboard | AUTH-001 | Pass (mocked)
A-02 | Sign-in | Success shown only after backend confirms | AUTH-009 | Pass (mocked)
A-03 | Sign-in | Login card disappears after navigation | AUTH-001; AUTH-010 | Pass (mocked)
A-04 | Sign-in | No app shell behind login card | AUTH-010 | Pass (mocked)
A-05 | Sign-in | Session survives refresh (8h validity) | AUTH-003 | Pass (mocked)
A-06 | Sign-in | Refresh on #/login with valid session | AUTH-011 | Pass (mocked)
A-07 | Sign-in | Open #/login while signed in | AUTH-002 | Pass (mocked)
A-08 | Sign-in | Transient network failure keeps session | AUTH-005 | Pass (mocked)
A-09 | Sign-in | Invalid session returns to login | AUTH-004 | Pass (mocked)
A-10 | Sign-in | Unregistered Google account handled honestly | AUTH-012 | Pass (mocked)
A-11 | Sign-in | Identity-recovery login for recovered user | AUTH-013 | Blocked
A-12 | RBAC | ADMIN sees all sections | AUTH-014 | Pass (mocked)
A-13 | RBAC | Limited role sees only permitted sections | AUTH-014 | Pass (mocked)
A-14 | RBAC | ADMIN-only actions gated | AUTH-008; ADMIN-004 | Pass (mocked) ¦ Retest
B-01 | Shelter Homes | Preview requires a valid URL | HOME-011 | Pass (mocked)
B-02 | Shelter Homes | Detected metadata values display | HOME-001 | Pass (mocked)
B-03 | Shelter Homes | Caretaker contact never the official contact | HOME-003 | Pass (mocked)
B-04 | Shelter Homes | Explicit contact prefilled | HOME-012 | Pass (mocked)
B-05 | Shelter Homes | Only missing fields prompt | HOME-002 | Pass (mocked)
B-06 | Shelter Homes | Invalid URL error | HOME-009; HOME-013 | Not Run ¦ Pass (mocked)
B-07 | Shelter Homes | Inaccessible sheet error | HOME-009 | Pass (mocked)
B-08 | Shelter Homes | No spreadsheet id exposed | HOME-014 | Pass (mocked)
C-01 | Connect & import | Fresh connect succeeds | HOME-004; IMPORT-001 | Pass (mocked)
C-02 | Connect & import | Connect success + import failure distinct | HOME-005 | Pass (mocked)
C-03 | Connect & import | Retry sync reuses identity, no duplicates | HOME-006 | Pass (mocked)
C-04 | Connect & import | Already-connected active source | HOME-007 | Pass (mocked)
C-05 | Connect & import | Archived source handled | HOME-008 | Pass (mocked)
C-06 | API errors | HTTP 404 / non-JSON never success | API-001 | Pass (mocked)
C-07 | Connect & import | Ambiguous failure re-checks homes | HOME-015 | Pass (mocked)
D-01 | Status display | Friendly status labels, no raw codes | HOME-016 | Pass (mocked)
D-02 | Status display | Contact updates without full refresh | HOME-010 | Blocked
D-03 | Status display | Technical detail stays in diagnostics | API-005 | Pass (mocked)
E-01 | Archive | Archive impact preview truthful | ADMIN-001 | Pass (mocked)
E-02 | Archive | Archive removes home from active list | ADMIN-002 | Pass (mocked)
E-03 | Archive | Archived participants leave rosters | EVENT-003 | Not Run
E-04 | Archive | Protected writes rejected clearly | ATT-007 | Pass (mocked)
E-05 | Archive | Restore returns the home | ADMIN-003 | Pass (mocked)
E-06 | Archive | History preserved after archive | ADMIN-006 | Blocked
F-01 | Attendance | Saved attendance displays on load | ATT-001 | Pass (mocked)
F-02 | Attendance | Mark persists and survives refresh | ATT-002; ATT-003 | Pass (mocked)
F-03 | Attendance | Idempotent identical re-save | ATT-004 | Pass (mocked)
F-04 | Attendance | Update uses expectedVersion | ATT-005 | Pass (mocked)
F-05 | Attendance | VERSION_CONFLICT recovery | ATT-006 | Pass (mocked)
F-06 | Attendance | Failed save never shows success | ATT-009 | Pass (mocked)
F-07 | Attendance | Archived/ineligible backend rejection | ATT-007 | Pass (mocked)
G-01 | Sync All | Job starts with real id and progress | SYNC-007 | Blocked
G-02 | Sync All | No duplicate job on refresh | SYNC-007 | Blocked
G-03 | Sync All | Accurate counts | SYNC-007 | Blocked
G-04 | Sync All | Archived homes excluded | SYNC-007 | Blocked
G-05 | Sync All | Cache updated after completion | SYNC-007 | Blocked
H-01 | Reliability | Retry buttons issue real new requests | API-003; ATT-008 | Pass (mocked)
H-02 | Reliability | Existing data stays visible / honest on refresh | DATA-005 | Pass (mocked)
H-03 | Reliability | No duplicate or stale requests | PERF-001; API-002 | Not Run
I-01 | Settings | User management (ADMIN) | ADMIN-005 | Not Run
I-02 | Reports | Reports load with real data | REPORT-001 | Not Run
J-01 | Regression | Login / RBAC / logout intact | AUTH-002; AUTH-006 | Pass (mocked)
J-02 | Regression | Rename sheet-sync verdicts truthful | SYNC-005 | Blocked
J-03 | Regression | Participant summaries correct | PART-001; PART-003 | Not Run ¦ Pass (mocked)
X-01 | Two-way sync | Sheet -> app participant sync | SYNC-001; SYNC-008; SYNC-009 | Blocked
X-02 | Two-way sync | App -> sheet write-back and rename | SYNC-002; SYNC-003; SYNC-004; DATA-002 | Blocked ¦ Not Run
X-03 | Security | Unauthenticated API access rejected | API-004 | Not Run
X-04 | Security | Credential/token hygiene | SEC-001 | Pass (mocked)
X-05 | Security | XSS resistance of rendered data | SEC-002 | Not Run
X-06 | Accessibility | Automated axe smoke on key routes | A11Y-001 | Pass (mocked)
X-07 | Accessibility | Keyboard-only navigation | A11Y-002 | Not Run
X-08 | Accessibility | Screen-reader spot check | A11Y-003 | Not Run
X-09 | Responsive | No horizontal overflow (desktop/tablet/mobile) | RESP-001 | Pass (mocked)
X-10 | Responsive | Mobile navigation drawer | RESP-002 | Pass (mocked)
X-11 | Browsers | Desktop Chromium E2E pass | COMP-003 | Pass (mocked)
X-12 | Browsers | Mobile emulation pass | COMP-004 | Pass (mocked)
X-13 | Browsers | Tablet emulation pass | COMP-005 | Pass (mocked)
X-14 | Browsers | Real device validation | COMP-006 | Not Run
X-15 | Concurrency | Multi-user simultaneous writes | COMP-002; PART-007; ATT-006; SCORE-002 | Not Run ¦ Pass (mocked)
X-16 | Performance | Request fan-out / N+1 | PERF-001 | Not Run
X-17 | Performance | Loading terminal states | PERF-002 | Retest
X-18 | Data integrity | Duplicate prevention across operations | DATA-001 | Not Run
X-19 | Data integrity | Audit history | DATA-003 | Not Run
X-20 | Data integrity | Production safety | DATA-004 | Not Run
X-21 | Backend contract | Schema/routes match frontend actions | COMP-001 | Not Run
X-22 | Scoring | Score persistence & conflicts | SCORE-001; SCORE-002; SCORE-003 | Not Run
X-23 | Teams | Team membership persistence & gates | TEAM-001; TEAM-002 | Not Run
X-24 | Results | Results consistency with scores | RESULT-001 | Not Run
X-25 | Certificates | Certificate flow | CERT-001 | Not Run
X-26 | Events | Event master & rosters | EVENT-001; EVENT-002; EVENT-003 | Not Run ¦ Pass (mocked)